## Sheet1
Assembly Line | SOA No. | SR.No. | Assembly Date | Unique Code | Splitted Code | Party | Customer PO No. | Code No | Product | Po Qty | Qty | Qty Exe. | Qty Pending | Finished Valve | GM Logo | Name Plate | Special Notes | Product Spcl 1 | Product Spcl 2 | Product Spcl 3 | Inspection | Painting | Delivery Date | Remarks
A | SOA0081 | 3 | 2026-05-01 |  |  | Reliance Industries Ltd. | 366/241062051 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 224 | 224 | 0 | 224 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL ( TUV TPI WO no-202_230196916 ) | Y | 2026-09-25
A | SOA0103 | 22 | 2026-05-01 |  |  | Reliance Industries Ltd. | 938/241066800 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 234 | 234 | 0 | 234 |  | GM | GM |  |  | Utility | NABL Lab tests Require | RIL | Y | 2026-08-08
A | SOA5813 | 2 | 2026-05-01 |  |  | Sunford Valve Company | 969 | 25GT8A6T1C1H1 | 25MM-GTV-800#-A105N-SWXBSP-T1(SS410)-B7/2H-HREG | 250 | 250 | 0 | 250 |  | NIBR:-SF, IBR:-GM | NIBR:-SF, IBR:-GM |  |  |  |  | N | N | 2026-04-27