## Sheet1
Assembly Line | SOA No. | SR.No. | Assembly Date | Unique Code | Splitted Code | Party | Customer PO No. | Code No | Product | Po Qty | Qty | Qty Exe. | Qty Pending | Finished Valve | GM Logo | Name Plate | Special Notes | Product Spcl 1 | Product Spcl 2 | Product Spcl 3 | Inspection | Painting | Delivery Date | Remarks
D | SOA0023 | 1 | 2026-04-16 |  |  | ARD Systems INC | P0001384 | 15GT8A1T2C1H2S2 | 15MM-GTV-800#-A105N-SW-T2(SS304)-B7/2H-HBLK-LOCKING ARR. | 6 | 6 | 0 | 6 | YES | GM | GM |  |  | SVS | 15GT8A1T1C1H1S2 | - | N | 2026-04-11
D | SOA0023 | 2 | 2026-04-16 |  |  | ARD Systems INC | P0001384 | 25GT8A1T2C1H2S2 | 25MM-GTV-800#-A105N-SW-T2(SS304)-B7/2H-HBLK-LOCKING ARR. | 6 | 6 | 0 | 6 | YES | GM | GM |  |  | SVS | 25GT8A1T1C1H1S2 | - | N | 2026-04-11
D | SOA0023 | 3 | 2026-04-16 |  |  | ARD Systems INC | P0001384 | 40GT1A9T2C1H2S2 | 40MM-GTV-150#-A105N-INTFE-T2(SS304)-B7/2H-HBLK-LOCKING ARR. | 1 | 1 | 0 | 1 |  | GM | GM |  |  |  |  | - | N | 2026-04-11
D | SOA0023 | 4 | 2026-04-16 |  |  | ARD Systems INC | P0001384 | 50GT1A9T2C1H2S2S3 | 50MM-GTV-150#-A105N-INTFE-T2(SS304)-B7/2H-HBLK-LOCKING ARR.-FULL BORE | 1 | 1 | 0 | 1 | YES | GM | GM |  | LOCKING KARVU | SVS | 50GT1A9T1C1H1S3 | - | N | 2026-04-11
D | SOA0023 | 5 | 2026-04-16 |  |  | ARD Systems INC | P0001384 | 15GB8A1T2C1H2 | 15MM-GBV-800#-A105N-SW-T2(SS304)-B7/2H-HBLK | 9 | 9 | 0 | 9 | YES | GM | GM |  |  | SVS | 15GB8A1T1C1H1 | - | N | 2026-04-11
D | SOA0023 | 6 | 2026-04-16 |  |  | ARD Systems INC | P0001384 | 25GB8A1T2C1H2 | 25MM-GBV-800#-A105N-SW-T2(SS304)-B7/2H-HBLK | 2 | 2 | 0 | 2 | YES | GM | GM |  |  | SVS | 25GB8A1T1C1H1 | - | N | 2026-04-11
D | SOA0027 | 1 | 2026-04-16 |  |  | John Crane Sealing Systems India Pvt. Ltd.-Bangalore | 4503426581 | 20GT9H1T12WBH2 | 20MM-GTV-1500#-LF2-SW-T12(SS316+HST6)-WELDED-HBLK | 8 | 8 | 0 | 8 |  | GM | GM |  | એરોનું ટપકું કાઢવું |  | IGC test req.,FET - ISO 15848 - PART 1 Class CH,PMI FOR BODY - BONNET | N | N | 2026-05-25
D | SOA0049 | 2 | 2026-04-16 |  |  | G M Engineering Pvt. Ltd. | LOI- 04-04-2026 | 25GT8A1T8C1H2 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HBLK | 100 | 100 | 0 | 100 | YES | GM | GM |  |  | SVS | 25GT8A1T1C1H1 | - | N | 2026-04-25
D | SOA0049 | 3 | 2026-04-16 |  |  | G M Engineering Pvt. Ltd. | LOI- 04-04-2026 | 15GT8A1T8C1H2 | 15MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HBLK | 30 | 30 | 0 | 30 | YES | GM | GM |  |  | SVS | 15GT8A1T1C1H1 | - | N | 2026-04-25
D | SOA0049 | 4 | 2026-04-16 |  |  | G M Engineering Pvt. Ltd. | LOI- 04-04-2026 | 20GB8A1T8C1H2 | 20MM-GBV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HBLK | 60 | 60 | 0 | 60 | YES | GM | GM |  |  | SVS | 20GB8A1T1C1H1 | - | N | 2026-04-25
D | SOA0056 | 1 | 2026-04-16 |  |  | Techsquad Engineering | TSE/1001-2025-26 | 15GT3A4T1C1H2S2 | 15MM-GTV-300#-A105N-WOFE-T1(SS410)-B7/2H-HBLK-LOCKING ARR. | 10 | 10 | 0 | 10 |  | GM | GM |  | TESTING 100% KARJO PELA COMPLAIN AAVEL CHE |  |  | - | Y | 2026-05-20
D | SOA0056 | 2 | 2026-04-16 |  |  | Techsquad Engineering | TSE/1001-2025-26 | 15GT1A4T1C1H2S2 | 15MM-GTV-150#-A105N-WOFE-T1(SS410)-B7/2H-HBLK-LOCKING ARR. | 32 | 32 | 0 | 32 |  | GM | GM |  | TESTING 100% KARJO PELA COMPLAIN AAVEL CHE |  |  | - | Y | 2026-05-20
D | SOA0056 | 3 | 2026-04-16 |  |  | Techsquad Engineering | TSE/1001-2025-26 | 25GT1A4T1C1H2S2 | 25MM-GTV-150#-A105N-WOFE-T1(SS410)-B7/2H-HBLK-LOCKING ARR. | 10 | 10 | 0 | 10 |  | GM | GM |  | TESTING 100% KARJO PELA COMPLAIN AAVEL CHE |  |  | - | Y | 2026-05-20
D | SOA0056 | 4 | 2026-04-16 |  |  | Techsquad Engineering | TSE/1001-2025-26 | 50GT1A4T1C1H2S2 | 50MM-GTV-150#-A105N-WOFE-T1(SS410)-B7/2H-HBLK-LOCKING ARR. | 5 | 5 | 0 | 5 |  | GM | GM |  | TESTING 100% KARJO PELA COMPLAIN AAVEL CHE |  |  | - | Y | 2026-05-20
D | SOA0056 | 8 | 2026-04-16 |  |  | Techsquad Engineering | TSE/1001-2025-26 | 15GT1B4T2C7H2S2 | 15MM-GTV-150#-F304/L(SS304/L)-WOFE-T2(SS304)-B8CL2/8-HBLK-LOCKING ARR. | 3 | 3 | 0 | 3 |  | GM | GM |  | TESTING 100% KARJO PELA COMPLAIN AAVEL CHE |  |  | - | Y | 2026-05-20
D | SOA0062 | 1 | 2026-04-16 |  |  | Techsquad Engineering | TSE/1003-2025-26 | 15GT3A4T1C1H2S2 | 15MM-GTV-300#-A105N-WOFE-T1(SS410)-B7/2H-HBLK-LOCKING ARR. | 15 | 15 | 0 | 15 |  | GM | GM |  |  |  |  | - | Y | 2026-05-31
D | SOA0062 | 9 | 2026-04-16 |  |  | Techsquad Engineering | TSE/1003-2025-26 | 15GT8B2T2C7H2S2 | 15MM-GTV-800#-F304/L(SS304/L)-NPT-T2(SS304)-B8CL2/8-HBLK-LOCKING ARR. | 10 | 10 | 0 | 10 |  | GM | GM |  |  |  |  | - | Y | 2026-05-31
D | SOA0062 | 10 | 2026-04-16 |  |  | Techsquad Engineering | TSE/1003-2025-26 | 15GT1D9T10C8H2S2 | 15MM-GTV-150#-F316/L(SS316/L)-INTFE-T10(SS316)-B8MCL2/8M-HBLK-LOCKING ARR. | 13 | 13 | 0 | 13 |  | GM | GM |  |  |  |  | - | Y | 2026-05-31
D | SOA0062 | 11 | 2026-04-16 |  |  | Techsquad Engineering | TSE/1003-2025-26 | 25GT1B9T2C7H2S2 | 25MM-GTV-150#-F304/L(SS304/L)-INTFE-T2(SS304)-B8CL2/8-HBLK-LOCKING ARR. | 5 | 5 | 0 | 5 |  | GM | GM |  |  |  |  | - | Y | 2026-05-31
D | SOA0083 | 1 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272643 | 20GB8A1T5C1H2S32 | 20MM-GBV-800#-A105N-SW-T5(SS410+FST6)-B7/2H-HBLK-XYLAN COATED FASTENER | 2 | 2 | 0 | 2 |  | GM | GM |  | FUGITIVE TESTING AS PER API 624/622/EN 15848-2 |  |  | - | N | 2026-05-01
D | SOA0083 | 2 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272643 | 15GB8D1T16C3H2S32 | 15MM-GBV-800#-F316/L(SS316/L)-SW-T16(SS316+FST6)-B8M/8M-HBLK-XYLAN COATED FASTENER | 2 | 2 | 0 | 2 |  | GM | GM |  | FUGITIVE TESTING AS PER API 624/622/EN 15848-2 |  |  | - | N | 2026-05-01
D | SOA0083 | 3 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272643 | 20GT8D1T16C3H2S32 | 20MM-GTV-800#-F316/L(SS316/L)-SW-T16(SS316+FST6)-B8M/8M-HBLK-XYLAN COATED FASTENER | 4 | 4 | 0 | 4 |  | GM | GM |  | FUGITIVE TESTING AS PER API 624/622/EN 15848-2 |  |  | - | N | 2026-05-01
D | SOA0083 | 4 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272643 | 20GT8A1T5C1H2S32 | 20MM-GTV-800#-A105N-SW-T5(SS410+FST6)-B7/2H-HBLK-XYLAN COATED FASTENER | 2 | 2 | 0 | 2 |  | GM | GM |  | FUGITIVE TESTING AS PER API 624/622/EN 15848-2 |  |  | - | N | 2026-05-01
D | SOA0083 | 5 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272643 | 15GT8D1T16C3H2S32 | 15MM-GTV-800#-F316/L(SS316/L)-SW-T16(SS316+FST6)-B8M/8M-HBLK-XYLAN COATED FASTENER | 2 | 2 | 0 | 2 |  | GM | GM |  | FUGITIVE TESTING AS PER API 624/622/EN 15848-2 |  |  | - | N | 2026-05-01
D | SOA0083 | 6 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272643 | 15LCH8D1T16C3S32 | 15MM-LCHV-800#-F316/L(SS316/L)-SW-T16(SS316+FST6)-B8M/8M-XYLAN COATED FASTENER | 2 | 2 | 0 | 2 |  | GM | GM |  |  |  |  | - | N | 2026-05-01
D | SOA0092 | 1 | 2026-04-16 |  |  | Technel Engineers | RM-202600010 | 20GT8D82T10C3H2 | 20MM-GTV-800#-F316/L(SS316/L)-NPTXBW80-T10(SS316)-B8M/8M-HBLK | 46 | 46 | 0 | 46 |  | GM | GM |  | IGC E , NACE |  |  | - | N | 2026-05-04
D | SOA0092 | 2 | 2026-04-16 |  |  | Technel Engineers | RM-202600010 | 15LCH8D12T10C3S42 | 15MM-LCHV-800#-F316/L(SS316/L)-BW80-T10(SS316)-B8M/8M-LOW TENSION SPRING | 8 | 8 | 0 | 8 |  | GM | GM |  | IGC E , NACE |  |  | - | N | 2026-05-04
D | SOA0092 | 3 | 2026-04-16 |  |  | Technel Engineers | RM-202600010 | 20LCH8D12T10C3S42 | 20MM-LCHV-800#-F316/L(SS316/L)-BW80-T10(SS316)-B8M/8M-LOW TENSION SPRING | 6 | 6 | 0 | 6 |  | GM | GM |  | IGC E , NACE |  |  | - | N | 2026-05-04
D | SOA0092 | 6 | 2026-04-16 |  |  | Technel Engineers | RM-202600010 | 20GB9D12T10WBH2S2 | 20MM-GBV-1500#-F316/L(SS316/L)-BW80-T10(SS316)-WELDED-HBLK-LOCKING ARR. | 8 | 8 | 0 | 8 |  | GM | GM |  | IGC E , NACE |  |  | - | N | 2026-05-04
D | SOA0097 | 2 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272768 | 15GT8AG1T13C3H2 | 15MM-GTV-800#-F20-SW-T13(F20)-B8M/8M-HBLK | 2 | 2 | 0 | 2 |  | GM | GM |  |  |  |  | - | N | 2026-06-25
D | SOA0097 | 3 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272768 | 15GT8B1T2C2H2 | 15MM-GTV-800#-F304/L(SS304/L)-SW-T2(SS304)-B8/8-HBLK | 4 | 4 | 0 | 4 | YES | GM | GM |  |  | SVS | 15GT8B1T2C2H1 | - | N | 2026-06-10
D | SOA0097 | 4 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272768 | 20GT8A1T5C1H2S32 | 20MM-GTV-800#-A105N-SW-T5(SS410+FST6)-B7/2H-HBLK-XYLAN COATED FASTENER | 11 | 11 | 0 | 11 |  | GM | GM |  | Fugitive Testing - As per API 624/622/ EN 15848-2 |  |  | - | N | 2026-06-10
D | SOA0097 | 5 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272768 | 15GB8D1T16C3H2S32 | 15MM-GBV-800#-F316/L(SS316/L)-SW-T16(SS316+FST6)-B8M/8M-HBLK-XYLAN COATED FASTENER | 2 | 2 | 0 | 2 |  | GM | GM |  | Fugitive Testing - As per API 624/622/ EN 15848-2 |  |  | - | N | 2026-06-10
D | SOA0097 | 6 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272768 | 20GB8A1T5C1H2S32 | 20MM-GBV-800#-A105N-SW-T5(SS410+FST6)-B7/2H-HBLK-XYLAN COATED FASTENER | 4 | 4 | 0 | 4 |  | GM | GM |  | Fugitive Testing - As per API 624/622/ EN 15848-2 |  |  | - | N | 2026-06-10
D | SOA0097 | 7 | 2026-04-16 |  |  | Flowserve India Controls Pvt. Ltd. (Pump Division) | 272768 | 20GT8D1T16C3H2S32 | 20MM-GTV-800#-F316/L(SS316/L)-SW-T16(SS316+FST6)-B8M/8M-HBLK-XYLAN COATED FASTENER | 4 | 4 | 0 | 4 |  | GM | GM |  | Fugitive Testing - As per API 624/622/ EN 15848-2 |  |  | - | N | 2026-06-10
D | SOA0102 | 1 | 2026-04-16 |  |  | Siemens Energy Industrial Turbomachinery India Pvt. Ltd. | 4510266193 | 20GT8A1T16C4H2 | 20MM-GTV-800#-A105N-SW-T16(SS316+FST6)-B7M/2HM-HBLK | 2 | 2 | 0 | 2 |  | GM | GM |  | ઓઇલ કરવું નહીં |  |  | - | N | 2026-06-30
D | SOA0102 | 2 | 2026-04-16 |  |  | Siemens Energy Industrial Turbomachinery India Pvt. Ltd. | 4510266193 | 25GT8A1T16C4H2 | 25MM-GTV-800#-A105N-SW-T16(SS316+FST6)-B7M/2HM-HBLK | 4 | 4 | 0 | 4 |  | GM | GM |  | ઓઇલ કરવું નહીં |  |  | - | N | 2026-06-30
D | SOA0112 | 1 | 2026-04-16 |  |  | Technel Engineers | RM-202500500 | 20LCH8D13T10C3 | 20MM-LCHV-800#-F316/L(SS316/L)-BW160-T10(SS316)-B8M/8M | 2 | 2 | 0 | 2 |  | GM | GM |  | IGC E | NACE |  | - | N | 2026-04-28
D | SOA0112 | 2 | 2026-04-16 |  |  | Technel Engineers | RM-202500500 | 20GT8D13T10C3H2S2 | 20MM-GTV-800#-F316/L(SS316/L)-BW160-T10(SS316)-B8M/8M-HBLK-LOCKING ARR. | 4 | 4 | 0 | 4 |  | GM | GM |  | IGC E | NACE |  | - | N | 2026-04-28
D | SOA0112 | 3 | 2026-04-16 |  |  | Technel Engineers | RM-202500500 | 15GT8D13T10C3H2 | 15MM-GTV-800#-F316/L(SS316/L)-BW160-T10(SS316)-B8M/8M-HBLK | 2 | 2 | 0 | 2 |  | GM | GM |  | IGC E | NACE |  | - | N | 2026-04-28
D | SOA0112 | 4 | 2026-04-16 |  |  | Technel Engineers | RM-202500500 | 20GT8D13T10C3H2 | 20MM-GTV-800#-F316/L(SS316/L)-BW160-T10(SS316)-B8M/8M-HBLK | 8 | 8 | 0 | 8 |  | GM | GM |  | IGC E | NACE |  | - | N | 2026-04-28
D | SOA0112 | 5 | 2026-04-16 |  |  | Technel Engineers | RM-202500500 | 20GT8AH13T40C3H2S2 | 20MM-GTV-800#-F60-BW160-T40(F60)-B8M/8M-HBLK-LOCKING ARR. | 4 | 4 | 0 | 4 |  | GM | GM |  | IGC E | NACE |  | - | N | 2026-04-28
D | SOA0115 | 1 | 2026-04-16 |  |  | YK Enterprises | PO NO YKE02/2026-27 | 40GT8A1T5C1H1 | 40MM-GTV-800#-A105N-SW-T5(SS410+FST6)-B7/2H-HREG | 18 | 18 | 0 | 18 |  | GM | GM |  | FULL URGENT | SVS | 40GT8A1T1C1H1 | - | N | 2026-04-21
D | SOA0115 | 2 | 2026-04-16 |  |  | YK Enterprises | PO NO YKE02/2026-27 | 25GB8A1T5C1H1 | 25MM-GBV-800#-A105N-SW-T5(SS410+FST6)-B7/2H-HREG | 1 | 1 | 0 | 1 |  | GM | GM |  | FULL URGENT | SVS | 25GB8A1T1C1H1 | - | N | 2026-04-21
D | SOA0115 | 3 | 2026-04-16 |  |  | YK Enterprises | PO NO YKE02/2026-27 | 40GB8A1T5C1H1 | 40MM-GBV-800#-A105N-SW-T5(SS410+FST6)-B7/2H-HREG | 1 | 1 | 0 | 1 |  | GM | GM |  | FULL URGENT | SVS | 40GB8A1T1C1H1 | - | N | 2026-04-21
D | SOA0115 | 4 | 2026-04-16 |  |  | YK Enterprises | PO NO YKE02/2026-27 | 40LCH8A1T5C1 | 40MM-LCHV-800#-A105N-SW-T5(SS410+FST6)-B7/2H | 1 | 1 | 0 | 1 |  | GM | GM |  | FULL URGENT | SVS | 40LCH8A1T1C1 | - | N | 2026-04-21
D | SOA0118 | 1 | 2026-04-16 |  |  | Ampo Valves India Pvt.Ltd. | 25/1437 | 25LCH8A1T16C1 | 25MM-LCHV-800#-A105N-SW-T16(SS316+FST6)-B7/2H | 12 | 12 | 0 | 12 |  | POYAM | GM |  |  | PLUG ST.6 |  | Y | N | 2026-04-28
D | SOA0124 | 1 | 2026-04-16 |  |  | John Crane Sealing Systems India Pvt. Ltd.-Pune | 4503436199 | 20LCH8D1T12C3 | 20MM-LCHV-800#-F316/L(SS316/L)-SW-T12(SS316+HST6)-B8M/8M | 2 | 2 | 0 | 2 |  | GM | GM |  | IGC test req.,PMI FOR BODY - BONNET | SVS | 20LCH8D1T10C3 | N | N | 2026-06-08
D | SOA0124 | 2 | 2026-04-16 |  |  | John Crane Sealing Systems India Pvt. Ltd.-Pune | 4503436199 | 20GT8D1T12C3H2 | 20MM-GTV-800#-F316/L(SS316/L)-SW-T12(SS316+HST6)-B8M/8M-HBLK | 8 | 8 | 0 | 8 |  | GM | GM |  | એરોનું ટપકું કાઢવું | SVS | 20GT8D1T10C3H1 | N | N | 2026-06-08
D | SOA4762 | 2 | 2026-04-16 |  |  | Enpro Industries Pvt. Ltd. | SED 4525012351 | 25GT8D12T12C8H2S3 | 25MM-GTV-800#-F316/L(SS316/L)-BW80-T12(SS316+HST6)-B8MCL2/8M-HBLK-FULL BORE | 12 | 12 | 0 | 12 |  | GM | GM |  | એરોનું ટપકું કાઢવું. |  | SEATRING ST.6 | Y | N | 2026-04-30
D | SOA4762 | 7 | 2026-04-16 |  |  | Enpro Industries Pvt. Ltd. | SED 4525012351 | 25GT8D12T12C8H2S2S3 | 25MM-GTV-800#-F316/L(SS316/L)-BW80-T12(SS316+HST6)-B8MCL2/8M-HBLK-LOCKING ARR.-FULL BORE | 15 | 15 | 0 | 15 |  | GM | GM |  | એરોનું ટપકું કાઢવું. |  | SEATRING ST.6 | Y | N | 2026-04-30
D | SOA5186 | 4 | 2026-04-16 |  |  | Flowserve Sanmar Private Limited | 6120002260 | 20LCH0D9T16WBS3 | 20MM-LCHV-2500#-F316/L(SS316/L)-INTFE-T16(SS316+FST6)-WELDED-FULL BORE | 8 | 8 | 0 | 8 |  | GM | GM |  | Testing 100% Hydro & Pneumatic Req. | NACE, IGC "E" |  | n | N | 2026-05-30
D | SOA5429 | 5 | 2026-04-16 |  |  | Technel Engineers | RM-202500500 | 20GT8AH13T40C3H2S2 | 20MM-GTV-800#-F60-BW160-T40(F60)-B8M/8M-HBLK-LOCKING ARR. | 28 | 28 | 0 | 28 |  | GM | GM |  | NACE, IGC "E" |  |  | N | N | 2026-05-10