## Sheet1
Assembly Line | SOA No. | SR.No. | Assembly Date | Unique Code | Splitted Code | Party | Customer PO No. | Code No | Product | Po Qty | Qty | Qty Exe. | Qty Pending | Finished Valve | GM Logo | Name Plate | Special Notes | Product Spcl 1 | Product Spcl 2 | Product Spcl 3 | Inspection | Painting | Delivery Date | Remarks
A | SOA0069 | 1 | 2026-04-26 |  |  | Reliance Industries Ltd. | 25G/241060825 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 25 | 25 | 0 | 25 |  | GM | GM |  |  |  | NABL Lab tests Require | RIL (TUV FO/ WO No : 280079885 ) | N | 2026-07-31
A | SOA0069 | 2 | 2026-04-26 |  |  | Reliance Industries Ltd. | 25G/241060825 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 30 | 30 | 0 | 30 |  | GM | GM |  |  |  | NABL Lab tests Require | RIL (TUV FO/ WO No : 280079885 ) | N | 2026-07-31
A | SOA0069 | 3 | 2026-04-26 |  |  | Reliance Industries Ltd. | 25G/241060825 | 20GB8A1T8C1H1P3 | 20MM-GBV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 3 | 3 | 0 | 3 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL (TUV FO/ WO No : 280079885 ) | N | 2026-07-31
A | SOA0070 | 1 | 2026-04-26 |  |  | Reliance Syngas Limited-SEZ | 25F/241061654 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 12 | 12 | 0 | 12 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | N | 2026-08-28
A | SOA0070 | 2 | 2026-04-26 |  |  | Reliance Syngas Limited-SEZ | 25F/241061654 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 10 | 10 | 0 | 10 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | N | 2026-08-28
A | SOA0071 | 1 | 2026-04-26 |  |  | Reliance Industries Limited-SEZ | 25F/241061638 | 40GT8A1T8C1H1P3 | 40MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 9 | 9 | 0 | 9 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL (TUV- TPI- FO NO 202_280063260) | Y | 2026-08-30
A | SOA0071 | 2 | 2026-04-26 |  |  | Reliance Industries Limited-SEZ | 25F/241061638 | 20GT8D1T10C8H1P3 | 20MM-GTV-800#-F316/L(SS316/L)-SW-T10(SS316)-B8MCL2/8M-HREG-PTEADIT | 16 | 16 | 0 | 16 |  | GM | GM |  | ઓઇલ કરવું નહીં | - | NABL Lab tests Require | RIL (TUV- TPI- FO NO 202_280063260) | Y | 2026-08-30
A | SOA0071 | 3 | 2026-04-26 |  |  | Reliance Industries Limited-SEZ | 25F/241061638 | 20GT8D1T10C8H1P3 | 20MM-GTV-800#-F316/L(SS316/L)-SW-T10(SS316)-B8MCL2/8M-HREG-PTEADIT | 9 | 9 | 0 | 9 |  | GM | GM |  | ઓઇલ કરવું નહીં | - | NABL Lab tests Require | RIL (TUV- TPI- FO NO 202_280063260) | Y | 2026-08-30
A | SOA0071 | 4 | 2026-04-26 |  |  | Reliance Industries Limited-SEZ | 25F/241061638 | 20GT8A5T8C1H1P3 | 20MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 33 | 33 | 0 | 33 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL (TUV- TPI- FO NO 202_280063260) | Y | 2026-08-30
A | SOA0072 | 1 | 2026-04-26 |  |  | Reliance Industries Ltd. | PPTA/25G/241060578 | 15GT8A5T8C1H1P3 | 15MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 3 | 3 | 0 | 3 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | N | 2026-07-31
A | SOA0072 | 2 | 2026-04-26 |  |  | Reliance Industries Ltd. | PPTA/25G/241060578 | 20GT8A5T8C1H1P3 | 20MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 7 | 7 | 0 | 7 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | N | 2026-07-31
A | SOA0072 | 6 | 2026-04-26 |  |  | Reliance Industries Ltd. | PPTA/25G/241060578 | 15GT8A5T8C1H1P3 | 15MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 6 | 6 | 0 | 6 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | N | 2026-07-31
A | SOA0072 | 7 | 2026-04-26 |  |  | Reliance Industries Ltd. | PPTA/25G/241060578 | 20GT8A5T8C1H1P3 | 20MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 4 | 4 | 0 | 4 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | N | 2026-07-31
A | SOA0072 | 8 | 2026-04-26 |  |  | Reliance Industries Ltd. | PPTA/25G/241060578 | 20GT8A5T8C1H1P3 | 20MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 2 | 2 | 0 | 2 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | N | 2026-07-31
A | SOA0072 | 9 | 2026-04-26 |  |  | Reliance Industries Ltd. | PPTA/25G/241060578 | 20GB8A1T8C1H1P3 | 20MM-GBV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 1 | 1 | 0 | 1 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | N | 2026-07-31
A | SOA0072 | 10 | 2026-04-26 |  |  | Reliance Industries Ltd. | PPTA/25G/241060578 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 4 | 4 | 0 | 4 |  | GM | GM |  |  | Utility | NABL Lab tests Require | RIL | N | 2026-07-31
A | SOA0072 | 11 | 2026-04-26 |  |  | Reliance Industries Ltd. | PPTA/25G/241060578 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 2 | 2 | 0 | 2 |  | GM | GM |  |  | Utility | NABL Lab tests Require | RIL | N | 2026-07-31
A | SOA0072 | 12 | 2026-04-26 |  |  | Reliance Industries Ltd. | PPTA/25G/241060578 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 1 | 1 | 0 | 1 |  | GM | GM |  |  | Utility | NABL Lab tests Require | RIL | N | 2026-07-31
A | SOA0073 | 1 | 2026-04-26 |  |  | Reliance Industries Ltd. | 25G/241060784 | 20GT8A5T8C1H1P3 | 20MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 1 | 1 | 0 | 1 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL ( TUV FO No.280051781 ) | N | 2026-07-31
A | SOA0073 | 2 | 2026-04-26 |  |  | Reliance Industries Ltd. | 25G/241060784 | 20GT8A5T8C1H1P3 | 20MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 9 | 9 | 0 | 9 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL ( TUV FO No.280051781 ) | N | 2026-07-31
A | SOA0074 | 1 | 2026-04-26 |  |  | Reliance Industries Ltd. | 25F/241063869 | 25GT8M1T8C16H1P3 | 25MM-GTV-800#-F5-SW-T8(SS410+HST6)-B16/7-HREG-PTEADIT | 2 | 2 | 0 | 2 |  | GM | GM |  | ઓઇલ કરવું નહીં | - | NABL Lab tests Require | RIL | Y | 2026-09-30
A | SOA0074 | 3 | 2026-04-26 |  |  | Reliance Industries Ltd. | 25F/241063869 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 2 | 2 | 0 | 2 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | Y | 2026-09-30
A | SOA0076 | 1 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061691 | 20GT8A5T8C1H1P3 | 20MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 3 | 3 | 0 | 3 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL (TUV TPI WO no-202_230179667 ) | N | 2026-09-25
A | SOA0077 | 1 | 2026-04-26 |  |  | Reliance Industries Limited - NMD | 366/241061631 | 25GT8O1T8C1H1P3 | 25MM-GTV-800#-A105N-IBR-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 9 | 9 | 0 | 9 |  | GM | GM |  |  | IBR | NABL Lab tests Require | RIL (TUV TPI WO no-202_230196916 ) | N | 2026-09-25
A | SOA0077 | 3 | 2026-04-26 |  |  | Reliance Industries Limited - NMD | 366/241061631 | 20GB8O1T8C1H1P3 | 20MM-GBV-800#-A105N-IBR-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 18 | 18 | 0 | 18 |  | GM | GM |  |  | IBR | NABL Lab tests Require | RIL (TUV TPI WO no-202_230196916 ) | N | 2026-09-25
A | SOA0077 | 4 | 2026-04-26 |  |  | Reliance Industries Limited - NMD | 366/241061631 | 40GT8O1T8C1H1P3 | 40MM-GTV-800#-A105N-IBR-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 13 | 13 | 0 | 13 |  | GM | GM |  |  | IBR | NABL Lab tests Require | RIL (TUV TPI WO no-202_230196916 ) | N | 2026-09-25
A | SOA0077 | 5 | 2026-04-26 |  |  | Reliance Industries Limited - NMD | 366/241061631 | 20GT8O5T8C1H1P3 | 20MM-GTV-800#-A105N-IBR-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 14 | 14 | 0 | 14 |  | GM | GM |  |  | IBR | NABL Lab tests Require | RIL (TUV TPI WO no-202_230196916 ) | N | 2026-09-25
A | SOA0078 | 1 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061692 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 11 | 11 | 0 | 11 |  | GM | GM |  |  | Utility | NABL Lab tests Require | RIL (TUV TPI WO no-Plant code - 39GP ) | Y | 2026-09-25
A | SOA0078 | 3 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061692 | 40GT8O1T8C1H1P3 | 40MM-GTV-800#-A105N-IBR-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 7 | 7 | 0 | 7 |  | GM | GM |  |  | IBR | NABL Lab tests Require | RIL (TUV TPI WO no-Plant code - 39GP ) | Y | 2026-09-25
A | SOA0078 | 5 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061692 | 40GT8O1T8C1H1P3 | 40MM-GTV-800#-A105N-IBR-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 2 | 2 | 0 | 2 |  | GM | GM |  |  | IBR | NABL Lab tests Require | RIL (TUV TPI WO no-Plant code - 39GP ) | Y | 2026-09-25
A | SOA0078 | 6 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061692 | 20BCH8O1T22C1 | 20MM-BCHV-800#-A105N-IBR-SW-T22(SS304+HST6)-B7/2H | 2 | 2 | 0 | 2 |  | GM | GM |  |  | IBR | NABL Lab tests Require | RIL (TUV TPI WO no-Plant code - 39GP ) | Y | 2026-09-25
A | SOA0078 | 7 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061692 | 20GT8A5T8C1H1P3 | 20MM-GTV-800#-A105N-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 3 | 3 | 0 | 3 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL (TUV TPI WO no-Plant code - 39GP ) | Y | 2026-09-25
A | SOA0078 | 9 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061692 | 20GT8B1T10C8H1P3 | 20MM-GTV-800#-F304/L(SS304/L)-SW-T10(SS316)-B8MCL2/8M-HREG-PTEADIT | 45 | 45 | 0 | 45 |  | GM | GM |  | ઓઇલ કરવું નહીં | - | NABL Lab tests Require | RIL (TUV TPI WO no-Plant code - 39GP ) | Y | 2026-09-25
A | SOA0078 | 11 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061692 | 25GT8A1T8C1H1P3 | 25MM-GTV-800#-A105N-SW-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 21 | 21 | 0 | 21 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL (TUV TPI WO no-Plant code - 39GP ) | Y | 2026-09-25
A | SOA0078 | 12 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061692 | 20GT8O5T8C1H1P3 | 20MM-GTV-800#-A105N-IBR-SWXNPT-T8(SS410+HST6)-B7/2H-HREG-PTEADIT | 11 | 11 | 0 | 11 |  | GM | GM |  |  | IBR | NABL Lab tests Require | RIL (TUV TPI WO no-Plant code - 39GP ) | Y | 2026-09-25
A | SOA0078 | 14 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241061692 | 20GT8B1T10C8H1P3 | 20MM-GTV-800#-F304/L(SS304/L)-SW-T10(SS316)-B8MCL2/8M-HREG-PTEADIT | 7 | 7 | 0 | 7 |  | GM | GM |  | ઓઇલ કરવું નહીં | - | NABL Lab tests Require | RIL (TUV TPI WO no-Plant code - 39GP ) | Y | 2026-09-25
A | SOA0156 | 2 | 2026-04-26 |  |  | Reliance Industries Ltd. | 366/241043899 | 20GT8A5T10C1H1P3 | 20MM-GTV-800#-A105N-SWXNPT-T10(SS316)-B7/2H-HREG-PTEADIT | 34 | 34 | 0 | 34 |  | GM | GM |  |  | - | NABL Lab tests Require | RIL | Y | 2026-10-30
A | SOA5014 | 4 | 2026-04-26 |  |  | Bharat Petroleum Corporation Ltd.-Mumbai | 4511423856 | 15GB8Z1T75C11H1 | 15MM-GBV-800#-F316H-SW-T75(SS316H+FST6)-660-HREG | 24 | 24 | 0 | 24 |  | GM | GM |  |  | H2 |  | Y | N | 2026-04-10
A | SOA5324 | 6 | 2026-04-26 |  |  | coxBRO Engineering Pvt Ltd | 250013 | 15GT8I1T69C8H1 | 15MM-GTV-800#-F321-SW-T69(F321+FST6)-B8MCL2/8M-HREG | 17 | 17 | 0 | 17 |  | BOS | N |  | એરોનું ટપકું કાઢવું. | WEDGE ST.6 |  | N | N | 2026-05-10
A | SOA5324 | 8 | 2026-04-26 |  |  | coxBRO Engineering Pvt Ltd | 250013 | 15GB8I1T69C8H1 | 15MM-GBV-800#-F321-SW-T69(F321+FST6)-B8MCL2/8M-HREG | 28 | 28 | 0 | 28 |  | BOS | N |  |  | PLUG ST.6 | NABL LAB TC REQ. | N | N | 2026-05-10
A | SOA5324 | 13 | 2026-04-26 |  |  | coxBRO Engineering Pvt Ltd | 250013 | 25GT8I1T69C8H1 | 25MM-GTV-800#-F321-SW-T69(F321+FST6)-B8MCL2/8M-HREG | 11 | 11 | 0 | 11 |  | BOS | N |  | એરોનું ટપકું કાઢવું. | WEDGE ST.6 |  | N | N | 2026-05-10
A | SOA5324 | 18 | 2026-04-26 |  |  | coxBRO Engineering Pvt Ltd | 250013 | 25LCH8I1T49C8 | 25MM-LCHV-800#-F321-SW-T49(F321+HST6)-B8MCL2/8M | 7 | 7 | 0 | 7 |  | BOS | N |  |  |  | NABL LAB TC REQ. | N | N | 2026-05-10
A | SOA5324 | 20 | 2026-04-26 |  |  | coxBRO Engineering Pvt Ltd | 250013 | 40GT8I1T69C8H1 | 40MM-GTV-800#-F321-SW-T69(F321+FST6)-B8MCL2/8M-HREG | 4 | 4 | 0 | 4 |  | BOS | N |  | એરોનું ટપકું કાઢવું. | WEDGE ST.6 |  | N | N | 2026-05-10